## Slide 1
Update Progress
Project Operations Directorate
PT Mitra Transaksi Indonesia

## Slide 2
Operational Technology Project
Progress
20 | 21
Live
20 | 21
Total Project
W3 | W4
Cancel
20 | 21
Project
REQUEST MITRATEX
5 | 3
149 | 149
142 | 145
1 | 1
Monitoring Closed Approved YOE Non LHF
SINGLE BTN
101
10
CLOSED APPROVED
SINGLE BMRI
IN MAAS
PENDING MAAS
111
SINGLE BNI
SINGLE BRI
0
39
0
50
SHARING
12
*Progress Request Mitratex akan selesai pada week 4
*Cancel untuk Scoring BTN,Bisa disetting saat tiket di analystnya BTN
CHANGEREQUEST MITRATEX
1 | 1
3 | 3
2 | 2
0 | 0
UAT
20 | 21
0 | 0
0 | 0

## Slide 3
Update Project Status – Highlighted Project
Hold
Progress
Live
Total Project
Drop
Project
UREQ
33
2
47
4
8
SR PROJECT
1
1
14
10
2
UARF
0
0
92
92
0
INCIDENT
25
1
66
27
13

## Slide 4
Update Project Status – Highlighted Project UREQ
Detail Project UREQ
Growth 2 pada progress
Summary Project By Week

## Slide 5
Update Project Status – Highlighted Project UARF
Growth 16 pada progress

## Slide 6
Update Project Status – Highlighted Project SR
Detail Project SR
Summary By Week
Growth 1 pada Done

## Slide 7
Update Project Status – Highlighted Project Incident
Detail Project Incident
Growth 2 pada Done

## Slide 8
Operational Technology Project

## Slide 9
Budget – Asset Planning

## Slide 10: Shortage EDC Base on Realistis Plan
Konven : 72.2K
BNI
-
BMRI
57.7K
Himbara
11.4K
Member Bank
3.1K
Buffer
-
Total : 144,4K
Android : 72.2K
BNI
22.8K
BMRI
-
Himbara
47.2K
Member Bank
2.1K
Buffer
-
*Note Konven :
Shortage EDC tersebut, akan dipenuhi pada tahap I sebanyak 70K, Sisanya disesuikan dengan kebutuhan Management MTI
Replace EDC Prio 1-4,
50% Prio 5-7 + NA
Asumsi 25% dari Remaining Target
Asumsi 20% dari Remaining Target
Kekurangan SPK 1 BNI Android (22.8K)
Tidak ada target Android
Asumsi 70% dari Remaining Target
BSI
Konven
Android

## Slide 11: EDC Stock Alocated

## Slide 12: EDC Stock Monitoring
Note : As of 29 Mei 2023, per end of Mei EDC APOS sudah di PO seluruhnya

## Slide 13: Procurement Monitoring
No | Procurement |  | Status | Due Date
1 | ECR L Shape 7K |  | Penilaian Teknis | 16 Juni 2023
2 | EDC Konven + Android 70K |  | Circulate Approval Budget | W2 Juli 2023
3 | Cartridge SAM Card dan SIM Card |  | Procurement Process | 16 Juni 2023
4 | Purchase Order 7.5K FMS Android DX8000 |  | Circulate Approval | 16 Juni 2023
5 | Perpanjangan Jasa MS Jadin & Mahapay |  | Drafting | W3 Juni 2023
6 | Purchase Order 3.8K FMS Android APOS A8 |  | Done | 9 Juni 2023
7 | LKI EDC Android DX8000 |  | Drafting | 16 Juni 2023
8 | Annual Support SKI FutureX |  | Pending, tidak masuk RKAP | -
9 | Purchase Order Ke-empat Sticker EDC |  | Done | 06 Juni 2023
10 | Purchase Order Implementasi Aplikasi ESTIM -YOE |  | Done | 08 Juni 2023
11 | Purchase Order Ke-lima Sticker EDC |  | Circulate Approval BoD | 15 Juni 2023
12 | Pengembangan Platform WABA |  | Addendum Process | 
13 | Thermal Paper |  |  | 
14 | License Tableau Explorer 2023 |  | Pending, Perlu PnL | 
15 | Jasa MS 118K |  | Negosiasi 3 Pemenang | 23 Juni 2023

## Slide 14: Payment or Budget Monitoring
No | Description |  | Status | Due Date
1 | SPKL Mei 2023 |  | Done | 09 Juni 2023
2 | Perdin Event Yogya Marathon |  | Done | 09 Juni 2023
3 | Perdin Event Java Jazz |  | Done | 09 Juni 2023
4 | Reimburse Pembelian Micro USB OTG |  | Finance Payment Process | 16 Juni 2023
5 | IP SAM Card Reader Ke-7 |  | Circulate Approval | 12 Juni 2023
6 | IP Indosat HiYokke Mei 2023 |  | Circulate Approval | 13 Juni 2023
7 |  |  |  | 
8 |  |  |  | 
9 |  |  |  | 
10 |  |  |  | 
11 |  |  |  | 

## Slide 15: Document Monitoring
No | Document |  | Status | Due Date
1 | Sertifikasi Kompetensi Bidang Sistem Pembayaran dan Pengelolaan Uang Rupiah (SPPUR) |  | Circulate Approval | 12 Juni 2023
2 |  |  |  | 
3 |  |  |  | 
4 |  |  |  | 
5 |  |  |  | 
6 |  |  |  | 
7 |  |  |  | 
8 |  |  |  | 
9 |  |  |  | 
10 |  |  |  | 
11 |  |  |  | 

## Slide 16: PKS / SPK / PP Monitoring
No | Document |  | Status | Due Date
1 | Addendum PKS Ke-empat BRI |  | Done | 
2 | PKS Re-peat Order BNI Konven 38K |  | Done | 
3 | PKS QRIS Acquirer |  | Pending, tidak ada underdoc | 
4 | PP Newland Konven |  | Negosiasi Ketentuan | 
5 | PP MS 60K |  |  | 
6 | PP EDC Move 28K |  |  | 
7 | PP EDC Move 15K |  |  | 

## Slide 17: Thermal Monitoring
Note : JNE masih menunggu report lanjutan (Sulawesi dan Papua)

## Slide 18: Thermal Monitoring
Note :
- Jan-23 - May-23 : Actual
- Jun-23 : Forcast

## Slide 19: TMS Android
No | Action |  | Status | Timeline
1 | Approach Vendor (12 Vendor) |  | Done | 
2 | Requirement List |  | Done | 
3 | Demo |  | Done | 
4 | Shortlist Vendor (3 Vendor) – (GST, CSNA dan Urovo) |  | Done | 
5 | SOW |  | Review | 
6 | Scenario POC |  | Done | 
7 | POC |  | Done | 
8 | Q n A After POC |  | On Schedule | 20 - 22 Jun 2023

## Slide 20
Proses Implementation &Resources Planning

## Slide 21
Process & Implementation Planning
Project Automation
RPA Robotic Fase 1
Refund Manual, Manual Posting, dan
Bulk Manual Posting
RPA Robotic Fase 2
Chargeback
Mobile Apps & E- Learning
Submit Ticket, Omnichanel, Live Chat, Telephony, ChatBot, TalkBot, LMS, Read FAQ, Reward Redeem, dan Gamification
Vendor Billing Recon
Reporting Activity Technician
Admin Fee EDC Recon
Warehouse Management System
Recon LinkAja Dynamic & Static

## Slide 22
Process & Implementation Planning
No. | Project Automation | Detail Project | PIC User | Update
1 | RPA Robotic Fase 1 | Refund Manual | Fadil | Testing OCR (17 sample surat diisi dengan manual)
 |  | Manual posting | Awal | 
 |  | Bulk Manual Posting | Ari | 
2 | RPA Robotic Fase 2 | Chargeback | Sandy | Request capture flow proses di MAAS
3 | Mobile Apps & E-Learnig | Submit Ticket | Bu Devi/Pak Ari | Review RFP
 |  | Omnichanel |  | 
 |  | Live Chat |  | 
 |  | Telephony |  | 
 |  | ChatBot |  | 
 |  | TalkBot |  | 
 |  | LMS |  | 
 |  | Read FAQ |  | 
 |  | Reward Redeem |  | 
 |  | Gamification |  | 
4 | Vendor Billing Recon |  | Mba Ikas | Gather Requirement
5 | Reporting Activity Technician |  | Mba Ikas | Gather Requirement
6 | Admin Fee EDC Recon |  | Mba Fifin | Gather Requirement
7 | Recon LinkAja Dynamic & Static |  | Mba Dewi | Gather Requirement
8 | Warehouse Management System |  | Team Aset | Not Started

## Slide 23
Operation Policies

## Slide 24: Thank you